## TestCase
Product Name |  | esquireqlectronics | TC Start Date | 09 August,2023 | TC Execution Start Date | 10 Agust,2023 |  |  |  |  | TEST CASE
Module Name |  | Sign Up, Sign IN | TC End Date | 09 August,2023 | TC Execution End Date | 10Agust,2023 |  |  |  |  | PASS | 69
Epic |  |  | Test Case Developed By | Faysal Miah | Browser (tested) | Yes |  |  |  |  | FAIL | 10
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  |  | Not Executed | 0
Test Executed by |  | Faysal Miah | [8 empty] | Out of Scope | 1
[11 empty] | TOTAL | 80
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Observed Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Go to different browsers 2. Go to the website "esquireelectronics.com" 3.Click on "Login" 4. Navigate "Register" Section |  |  | Passed
2 | User Management | UI Testing | Register | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Check for any grammatical or spelling mistake |  |  | Passed
3 |  |  |  | Verifying that full page is not showed up on the screen | Page should only show down to register section without scrolling | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Check the screen content |  |  | Passed
4 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Check all the font size , color and style |  |  | Passed
5 |  |  |  | Checking if the registration form has all the fields per the requirement document. | There should be required number of input field as per the requirement | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Check the input fields |  |  | Passed
6 |  |  |  | Verifying mandatory field is marked with a asterisk | asterisk should be present with filed label | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Check if all the mandatory fields are marked with asterisk |  |  | Passed
7 |  |  |  | Checking the placeholders | text should be in the field describing the field of input format | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Check all the input fields placeholders |  |  | Passed
8 |  |  |  | Checking alignment of the all the elements | Proper alignment of the fields should be present | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Check the allignment of elements like input fileds,labels etc |  |  | Passed
9 |  |  |  | Checking the avaibility of "Terms & conditions" and "Privacy Policy" 4.Check if ''Terms & condition'' and '''Privacy Policy' available | Should be two links on ""Terms and Condition" and "Privacy policy" | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Check if "Terms & Conditions" and "Privacy policy" exists |  |  | Passed
11 |  | Functional Testing |  | Verify by clicking on the "Sign Up" button for blank input. | Should show an error message and stop from registering | Found as per the expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.click on "Sign Up" button |  |  | Passed
12 |  |  |  | Verify that the user is able to click on all the input field or not | User should be able click on all the input field | Found as per the expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.click on all the input fields |  |  | Passed
13 |  |  |  | Verify that when the user clicks on the input field, the text cursor should be displayed | Cursor should be in input field | Found as per the expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.click on all the input fields |  |  | Passed
14 |  |  |  | Verify that News letter Subscriptuion is checked on by default | The newsletter chekbox should be cheked on by default | Found as per the expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 5.Navigate to check button for promotion and offer |  |  | Passed
15 |  |  |  | Checking the input length of phone number field | Should not be take any input greater than 11 characters and less than 11 characters | Found as per expectation | 14747471548 | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Chek the phone number field if it takes a 12 digits |  |  | Passed
16 |  |  |  | Cheking if the phone number filed accepts anything other than numeric inputs | Should not take any non numeric inputs | took any value as input | akbhdfhbufd, &^$#*&^$_*%&^, JHGJh546546Gfy | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Input anything non numeric value in pfone number field | Input Error |  | Failed
17 |  |  |  | Checking with special chracters as input in phone number field | Should not allow to sign up and show a error message | Found as per expectation | #*&!$, $@)@&, ^%$(*^&$^& | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Input special characters in phone number field 5.Click on ''Sign Up" button |  |  | Passed
18 |  |  |  | Checking with alphabets as inputs in phone number | Should not allow to sign up and show a error message | Found as per expectation | ajhxtdguxts, audsud | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Input alphabtes in phone number field 5.Click on ''Sign Up" button |  |  | Passed
19 |  |  |  | Checking with mixed type of data as inputs in phone number | Should not allow to sign up and show a error message | Found as per expectation | ajsu48595#5, a4d5f8hhf9sx 87.9878.4 | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Input mixed data in phone number field 5.Click on ''Sign Up" button |  |  | Passed
20 |  |  |  | Checking with random numbers without any phone number format | Should not allow to sign up and show a error message | Aloowed to click on Sign Up button and asked for an otp send in that number | 00000010000, 00001900000 | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Input random digts without any phone number format | Random numbers error |  | Failed
21 |  |  |  | Checking with non Bangladeshi phone number | Should not allow to sign up and show a error message | Aloowed to click on Sign Up button and asked for an otp send in that number | 18332405104 | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Input any foreign number within 11 digits | Foreign Phone number error |  | Failed
22 |  |  |  | Checking with already registered phone number | Should not allow to sign up and show a error message | Found as per expectation | 178459865 | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill phone number field with a registered number 5. Filled other field with valid input 6.click on sign up |  |  | Passed
23 |  |  |  | Checking with valid phone number | Should allow to sign up and send an otp in that number | Found as per expectation | 1784598742 | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4. Fill all the input field with valid input .Click on Sign Up |  |  | Passed
24 |  |  |  | Checking with invalid email address | Should not accept the provided input and showing an error meesgae under email field | Found as per expectation | y@ydb@hb.com, jghvjujubub.edu, jhbgjubhbh@in, ihbuibhnibni, iniinuinrd@bhuihb | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Input an invalid email address in email field |  |  | Passed
25 |  |  |  | Checking with blank email field | Should not allow to sign up and show an error message | Allowed to use Sign Up button and send an otp to provided mobile number | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Keep email field blank 5.Fill all the other fields with valid inputs 6.Click on Sign Up | Empty email ss |  | Failed
26 |  |  |  | Checking with already registered email address | Should not allow to sign up and show an error message | Found as per expectation | test@gmail.cm | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill email field with a registered email address 5. Filled other field with valid input 6.click on sign up |  |  | Passed
27 |  |  |  | Checking Sign Up button functionality with invalid email address | Should not allow to sign up and show an error message | Found as per expectation | y@ydb@hb.com, jghvjujubub.edu, jhbgjubhbh@in, ihbuibhnibni, iniinuinrd@bhuihb | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Input an invalid email address in email field 5.Fill all the other fields with valid inputs 6.Click on Sign Up |  |  | Passed
28 |  |  |  | Verifying that the Days option if all the days available or not | option should be avialabe from 1 to 31 | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Click on Days |  |  | Passed
29 |  |  |  | Verifying that Months option if all the Months available or not | option should be avialabe from 1 to 12 | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Click on months |  |  | Passed
30 |  |  |  | Verifying that Years option if all the required Years available or not | All the years between 1940 to 2021 should be availbale in the option inclusively | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Click on Years |  |  | Passed
31 |  |  |  | Cheking with balnk Birthday | Should be allowed to sign up | Not allowed to sign up and make it madatory to fill up birthday field | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill up all the field except birthday 5. Click on Sign Up | Empty Birthday |  | Failed
32 |  |  |  | Checking with one blank field of birthday | Should not be allowed to sign up and show an error message | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill up all the field except any one field of birthday 5. Click on Sign Up |  |  | Passed
33 |  |  |  | Checking with two field of birthday | Should not be allowed to sign up and show an error message | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill up all the field except any two field of birthday 5. Click on Sign Up |  |  | Passed
34 |  |  |  | Checking with invalid date format | Should not be allowed to sign up and show an error message | Allowed any wrong combination of date | Day:31,Month:2,Year: 2010 | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Select 2 for month,31 for days and 2010 fro years 5.Fill all the other fields with valid inputs 6.Click on Sign Up | Invalid Date |  | Failed
35 |  |  |  | Verifying that Gender has all the options available as per the requirement | should be three option to choose from | Found as per the expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Click on Gender |  |  | Passed
36 |  |  |  | Checking without choosing any option from Gender | Should be allowed to sign up | Found as per the expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all fields except Gender |  |  | Passed
37 |  |  |  | Checking Sign up functionality with filling optional field only | Should not allowed tosign up and show an error message | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all optional fields only 5.Click on Sign Up |  |  | Passed
38 |  |  |  | Checking Sign up functionality with filling mandatory field only | Should be allowed to sign up | Not allowed to sign up and showed error messages to fill up the optional fields | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the mandatory fields only 5.Click on Sign Up | Empty optional field |  | Failed
39 |  |  |  | Checking Sign up with unchecked promotion checkfield | Should be allowed to sign up | Found as per the expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5. Unheck the promotion checkbox 6.Click on Sign Up |  |  | Passed
40 |  |  |  | Checking Sign up with checked promotion checkfield | Should be allowed to sign up | Found as per the expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5. Check the promotion checkbox 6.Click on Sign Up |  |  | Passed
41 |  |  |  | Veifying the option to sign up with google account | Should be able to sign up with google account | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Click on Google button under Sign Up With label |  |  | Passed
42 |  |  |  | Veifying the option to sign up with facebook account | Should accept the provided input | Found as per expectations | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Click on Facebook button under Sign Up With label |  |  | Passed
43 |  |  |  | Checking the Sign Up button functionality | Should be able to sign up with google account | Facebook signup unavailable for this app | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up | Facebook Sign Up |  | Out of Scope
44 |  |  |  | Checking otp send on provided mobile number | A sms containg otp should be send on given mobile number | Found as per expectations | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up 6.Sms send on given phone number |  |  | Passed
45 |  |  |  | Checking otp field after sign up | A windows should pop up with otp field after a successful sign up | Found as per expectations | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up |  |  | Passed
46 |  |  |  | Cheking otp input field | should be 6 input field for each character | Found as per expectations | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up 6.Check the pop up window |  |  | Passed
47 |  |  |  | Cheking by mutiple keyboard key pressing in a single filed | first character should be in the first field and the second one should be inputed in the next field | Found as per expectations | hh,kk.rf | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up 6.Check the pop up window 7.Slect the very first field 8.Now input data |  |  | Passed
48 |  |  |  | Cheking by mutiple keyboard key pressing in last field | if the otp become right then proced to next page if false then showing an error message and don't change the value of last field | Found as per expectations | jk,yfh.tertr | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up 6.Check the pop up window 7.Slect the very first field 8.Now input data untill the second field form last 9.Now press multiple key |  |  | Passed
49 |  |  |  | Checking clearing of the otp input field | shoulb clear the single field if selected and pressed backspace button | Very first field can't be cleared | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up 6.Check the pop up window 7.Input some invalid data 8.Now select each field and press backspace to clear the input | Otp Cleaning |  | Failed
50 |  |  |  | verifying the exit option on the otp window | Should a "x" or cancel button on the window | There is no option to cancel the otp field and the page has to refresh or wait for a certain time to get the window closed automatically | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up 6.Check for close or cansel option in window | Otp Close Option |  | Failed
51 |  |  |  | Checking with invalid otp | Should not take the input and show an error message | Found as per expectations | kjjd5d, #$*fd85,gvjuuj,48598/, 649885 | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up 6.Input invalid data in the popped window |  |  | Passed
52 |  |  |  | Checking the otp timer | A timer should start for 60 seconds and going backwards from 60 | Found as per expectations | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up 6.Observe the timer in popped window |  |  | Passed
53 |  |  |  | Checking otp timer timeout | After 60 seconds a Resend button should appear and timer should be disappered | Found as per expectations | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up 6.Observe the timer in popped window 7. After 60 second observe the difference |  |  | Passed
54 |  |  |  | Checking otp input type | otp filed should take any type of input | Found as per expectations | 134587, jhy ik,*7 54** | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up 6.Input various type of data as input |  |  | Passed
55 |  |  |  | Check Resend timeout | After certain failed attempts and resend the otp window should closed automatically and show an error message | Found as per expectations | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.Click on Sign Up 6. After 60 second timer timeout press the Resend button 7.Reapet step 6 for 3 times |  |  | Passed
55 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | voldemort, test@gmail.com , Ken Addams | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Select any field 5.Copy Paste input data https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
56 |  |  |  | Checking keyboards arrow buttons | Showld browse through the input | Functioning successfully | Use arrow keys in every fields input | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Select any field 5. input data 6.Use arrow keys to browse through data charcters https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
57 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Select any field 5.Press tab key https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Press tab key https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter tab in every field |  |  | Passed
58 |  |  |  | Checking keyboard enter button functionality | Should act as final submission/sign up | Functioning successfully | Input Enter in every field | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill all input field 5.press enter key https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
59 |  | UI Testing | Login | Checking spelling or grammatical mistakes | Sholud not be any spelling or gramatical error | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 4.Check for any grammatical or spelling mistake |  |  | Passed
60 |  |  |  | Verify that every field has placeholder | All the fields should have placehoder describing the fields | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 4.Observe every input fields placeholders |  |  | Passed
61 |  |  |  | Verifying that full page is not showed up on the screen | Only login section should be shown | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" |  |  | Passed
62 |  |  |  | Verifying the font, text color and style | Should be as per the expectations | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3.Observe all the font size, color,style |  |  | Passed
63 |  |  |  | Checking if the login form has all the elements per the requirement document. | Should be as per the expectations | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3.Observer all the elements like input fields ,lables ,buttons etc |  |  | Passed
64 |  |  |  | Verifying that there is a option to unmask the password | Should be an eye/or nay other icon in the password field to unmask the input data | There is no option to unmask the input value for password | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3.Click on Forget Password 4.Input valid phone number in phone number field 5.input otp send in mobile 4.input password in password and confirm password field 5.Observer any option to unmask the input value | Password Unmask |  | Failed
65 |  |  |  | Checking alignment of the fields | Should be as per the expectations | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3.Observer all the elements alignment |  |  | Passed
66 |  |  |  | Verifying that there is options available to reset password and to create a new account | "forget password'' and "Register Now" option should be available | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3.Look for 'forget password' and 'register now' |  |  | Passed
67 |  |  |  | verifying the option to login with different method | should be option to login with google or facebook account | Found as per expectation | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3.Look for Log in with 'google' and 'facebook' |  |  | Passed
68 |  | Functional Testing |  | Checking Login with Phone Number fields | Should not allow login and showed message to fill up the Phone number filed | Found as per expectations | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In' 3.Click on login with empty inputs |  |  | Passed
69 |  |  |  | Checking with unregistered Phone Number | Should not allow to login and show an error message | Found as per expectations | 01784596584, 01684687515 | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In' 3.Fill up Phone number field with unregistered number 4.Click on logini |  |  | Passed
70 |  |  |  | Checking with unregistered mobile | Should not allow to login and show an error message | Found as per expectations | 01789548624, Ad5s+4d5s | 1.Go to url ''esquireelectronics.com'' 2.Click on Sign In 3.Fill up phone number with unregistered mobile 4.Click on login |  |  | Passed
71 |  |  |  | checking login with wong value | Should not allow to login and show an error message | Found as per expectations | hello@my.com 58H*hjca, 26565656 | 1.Go to url ''esquireelectronics.com'' 2.Click on Sign In 3.Fill up phone number with invalid data 4.Click on login |  |  | Passed
72 |  |  |  | Checking the login with registered email in phone number field | Should not allow to login and show an error message | Found as per expectations | test@gmail.cm | 1.Go to url ''esquireelectronics.com'' 2.Click on Sign In 3.Fill up phone number with registered email 4.Click on login |  |  | Passed
73 |  |  |  | Checking the functionality of forget password | should lead user to another page and sent an sms to provided mobile numberl by user nad after entering the otp ,allow to create a new password | Found as per expectations | N/A | 1.Go to url ''esquireelectronics.com'' 2.Click on Sign In 3.click on forget password 4. Enter an registered mobile number 5.enter otp 6.create a new password |  |  | Passed
74 |  |  |  | Checking with valid and registered information | Should be a successful login and land into homepage | Found as per expectations | pickaboo@gmail.com pi4568Jhdn | 1.Go to url ''esquireelectronics.com'' 2.Click on Sign In 3.Fill up with valid info 4.Click on login |  |  | Passed
75 |  |  |  | Checking the functionality of 'Register' | Should lead to register page | Found as per expectations | N/A | 1.Go to url ''esquireelectronics.com'' 2.Click on Sign In 3.Click on Register |  |  | Passed
76 |  |  |  | Checking the functionality to log in with social media account | Should be able to log in with registered google or facebook account | Found as per expectations | N/A | 1.Go to url ''pickaboo.com'' 2.Click on Login 3.Click on Google/Facebook |  |  | Passed
77 |  | Usability Testing |  | Checking copy paste functionality in every field | Should allow to copy paste in all fields | Found as per expectations | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3.Select any field 5.Copy Paste input data https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
78 |  |  |  | Checking keyboards arrow buttons | Should allow browse through data with arrow keys | Found as per expectations | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3.Select any field 4. input data 5.Use arrow keys to browse through data charcters https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
79 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Found as per expectations | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3..Select any field 5.Press tab key https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Press tab key https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter tab in every field |  |  | Passed
80 |  |  |  | Checking keyboard enter button functionality | Should act as final submission | Act as a final submission | N/A | 1.Go to the website "esquireelectronics.com" 2.Click on "Sign In" 3. Click on "Register Now" 4.Fill Up all the fields 5.press enter key 6.Click on Sign Up |  |  | Passed
|  |  | Improvement Scope | A maximum length sohould be defined similar to registration section for eamil and password field
Remember me' option should be included in sign in page
There should be 'Login with Google ' and 'Login with Facebook' instead of just Google and Facebook
Erro message should not be said "A User with this phone or email no could not be found!" Since the only input available and that label as aphone number,The error message should not mention email .
Error message should be same whenever one filed or both field is incorrect
There should be a option to unmask the password option in when creating a password
there should be also option available to acces with email and password
Negative test

## Bug Report
Bug Report |  |  | Bug Report
#SL | 16 |  | #SL | 20
ISSUE | Phone number filed taking non numeric value |  | ISSUE | Phone number filed taking non numeric value
REPRODUCING STEPS | 1.Go to the website "esquireelectronics.com" |  | REPRODUCING STEPS | 1.Go to the website "esquireelectronics.com"
| 2.Click on "Sign In" |  |  | 2.Click on "Sign In"
| 3. Click on "Register Now" |  |  | 3. Click on "Register Now"
| 4.Input anything non numeric value in phone number field |  |  | 4.Input random digts without any phone number format
MODULE | Sign Up |  | MODULE | Sign Up
ENV | Production |  | ENV | Production
SS | Input Error |  | SS | Random numbers error
RESPONSIBLE QA | Hasan |  | RESPONSIBLE QA | Hasan
Bug Report
| #SL | 21
| ISSUE | Phone number field take valid foreign number as input
| REPRODUCING STEPS | 1.Go to the website "esquireelectronics.com"
2.Click on "Sign In"
3. Click on "Register Now"
4.Input valid foreign phone number in Phone number field
| MODULE | Sign Up
| ENV | Production
| SS | Foreign Phone number error
| RESPONSIBLE QA | Hasan

## Report
Test Case Report
Project Name | esquireelectronics.com
Module Name | Sign Up and Sign In |  |  |  |  | Total No. | Status | Result :
Test Case Version | 1.01 |  |  |  |  | 69 | PASS
Written By | Mahmudol Hasan Tushar |  |  |  |  | 10 | FAIL
Executed By | Mahmudo,l Hasan Tushar |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Reviewed By | [5 empty] | 1 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 69 | 10 | 0 | 1 | 80
Grand Total | 69 | 10 | 0 | 1 | 80
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (80/80)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/80)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (69/80)*100 = 86.25
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (10/80)*100 = 12.5
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/62)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A